## Working_file
Vendor/supplying plant | Material | Short Text | Quantity | Sched. Qty | Del. Date | To be del. | UoM | Purch.Doc. | PO Date | 2022-12-31 | <<- Today's Date
| 500264 | RM-AMMONIUM BICARBONATE | 202 | 202 | 2020-01-25 | 126 | MT | 4100095731 | 2020-07-01 | 1071
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926
44926

## 02.03.21
Pending PO's List:- | [7 empty] | PO-Summary (Delay in Delivery) |  | Counter:- |  |  |  | Plan changes Dec.// switch b/w Lines
[8 empty] | 0-10 Days | 25 | 0 |  |  |  | Instances where Idle MP due to shortage Pkg.
[8 empty] | 11-20 Days | 8 | 25 |  |  |  | MP being Idle in Dec.
[8 empty] | >20 Days | 47
[8 empty] | Total | 80
Vendor/supplying plant | Material | Short Text | Quantity | Sched. Qty | Del. Date | To be del. | UoM | Purch.Doc. | PO Date | Pending Since No. of days | Status | Revised Date | Material
| 500264 | RM-AMMONIUM BICARBONATE | 202 | 202 | 2020-01-25 | 126 | MT | 4100095731 | 2020-07-01 | 402 |  | 20.08.2020 | 605677
[10 empty] | 387 |  | 15.08.2020 | 605863
[10 empty] | 305 |  | 15.08.2020 | 605765
[10 empty] | 305 |  | 15.08.2020 | 605764
[10 empty] | 228 |  | 15.08.2020 | 605741
[10 empty] | 189 |  | 25.07.2020 | 605614
[10 empty] | 182 |  | 10.08.2020 | 605614
[10 empty] | 176 |  | 15.08.2020 | 605812
[10 empty] | 162 |  | 10.08.2020 | 606164
[10 empty] | 148 |  | 10.08.2020 | 605818
[10 empty] | 139 |  | 25.07.2020 | 605877
[10 empty] | 138 |  | 25.07.2020 | 605571
[10 empty] | 124 |  | Same
[10 empty] | 114 |  | Same
[10 empty] | 107 |  | 15.08.2020 | 605687
[10 empty] | 102 |  | Same
[10 empty] | 92 |  | 10.08.2020 | 605817
[10 empty] | 91 |  | Same
[10 empty] | 86 |  | Same
[10 empty] | 86 |  | Same
[10 empty] | 82 |  | Same
[10 empty] | 82 |  | Same
82
82
68
60
60
60
60
60
60
56
50
46
46
31
29
29
29
29
29
29
29
29
29
29
29
20
20
20
20
15
15
15
11
7
5
5
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1
1

## 17.02.21
Pending PO's List:- | [7 empty] | PO-Summary (Delay in Delivery) |  | Counter:- |  |  |  | Plan changes Dec.// switch b/w Lines
[8 empty] | 0-10 Days | 10 | 108 |  |  |  | Instances where Idle MP due to shortage Pkg.
[8 empty] | 11-20 Days | 18 | 118 |  |  |  | MP being Idle in Dec.
[8 empty] | >20 Days | 38
[8 empty] | Total | 66
Vendor/supplying plant | Material | Short Text | Quantity | Sched. Qty | Del. Date | To be del. | UoM | Purch.Doc. | PO Date | Pending Since No. of days | Status | Revised Date | Material
[10 empty] | 389 |  | 20.08.2020 | 605677
[10 empty] | 374 |  | 15.08.2020 | 605863
[10 empty] | 292 |  | 15.08.2020 | 605765
[10 empty] | 215 |  | 15.08.2020 | 605764
[10 empty] | 176 |  | 15.08.2020 | 605741
[10 empty] | 169 |  | 25.07.2020 | 605614
[10 empty] | 163 |  | 10.08.2020 | 605614
[10 empty] | 149 |  | 15.08.2020 | 605812
[10 empty] | 135 |  | 10.08.2020 | 606164
[10 empty] | 126 |  | 10.08.2020 | 605818
[10 empty] | 125 |  | 25.07.2020 | 605877
[10 empty] | 120 |  | 25.07.2020 | 605571
[10 empty] | 111 |  | Same
[10 empty] | 101 |  | Same
[10 empty] | 94 |  | 15.08.2020 | 605687
[10 empty] | 89 |  | Same
[10 empty] | 78 |  | 10.08.2020 | 605817
[10 empty] | 73 |  | Same
[10 empty] | 69 |  | Same
[10 empty] | 55 |  | Same
[10 empty] | 47 |  | Same
[10 empty] | 47 |  | Same
47
47
47
47
47
45
43
43
43
43
38
37
33
33
33
28
18
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
16
12
8
7
7
7
7
3
2
2
0
0
-2
-4
-8
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-12
-16
-16
-16
-16
-16
-36
-43
-43
-43
-43
-43
-43
-43
-43
-43
-43
-46
-47
-47
-47
-47
-47
-52
-52
-52
-57
-57
-57
-57
-62
-73
-73
-73
-73
-73
-73
-73
-73
-73
-73
-77
-77
-77
-82
-82
-82
-87
-104
-104
-104
-104
-108
-108
-108
-108
-108
-113
-113
-113
-134
-134
-134
-134
-134
-134
-134
-134
-165
-165
-165
-165
-165
-165
-165
-165
-196
-196
-196
-226
-227
-257
-257
-287
-287
-287